## Sheet1
Priority | Column1 | Issue | Issue Submitted | Who identified? | Approx Time to Resolve | Comment
Low |  |  | · For SITFL... check site status task is occuring before site inspector assignment. It would appear the the check site status should occur afterwards, as it entails DDD completion / concurrence, but the site inspection has not yet occured. | Root cause | Major fix because I don’t know how else it would work. | -Intentional, not a bug.
Low |  | · | · Applicant through PAGS Review in PARIS cannot be assigned to PDM until marked "Eligible" in EMMIE. The issue is that we have to wait until the EDW report refreshes in EMMIE the next day. This is causing a lag in assignments. | Root cause | -minor fix (may increase depending on how it will work otherwise) | One of the major issues identified during the January Denton Test was that ineligible applicants could still be moved forward. This was designed to prevent that, with the explicit warning at the time that it would cause this lag. It was my understanding that people agreed that it was an acceptable tradeoff.
Low |  | · | · When creating the Project shell in EMMIE from the data in PARIS, DIU is missing information to complete the Project Description tab's required fields. Need to add % complete and "as of" date to the PARIS form. | Root cause | minor to medium depending on fix | There needs to be an agreeance on how these are determined. Average of all sites with the last date from a site? Have PDM manually enter on Project?
High |  | · | · ​ ​There is no task in PARIS for DIU to upload an RFI request to EMMIE for permanent record. Request that a report be generated to identify when the RFi is transmitted so that DIU can add request to EMMIE. Currently there is no field in PARIS to indicate that DIU has completed upload. Date field will need to be added to the RFI screen to track when completed. Report could be cumulative and iinclude applcant name, project # and name, RFI #, RFI "date sent to applicant" and the Uploaded in EMMIE date. | Root cause | Minor | Need guidance on process.
Medium |  | · | · Need to create a field in RFI Processing, RFI Reciept for partial receipt of request. DIU was instructed not to use the Received Information - RFI complete unless all of the documents requested were addressed.DIU would update PARIS when partial receipt is received, field does not need to be date, can be "check mark" or "yes". Need to build RFI report to identify aging RFIs to include this partial field. | Root cause | medium
Medium |  | · | · Can DIU have a comment box in the PARIS DIU section (far right of tasks) so that we can add comments when we send tasks back to be reworked? | Root cause | minor | Could also be solved by fixing rework comments altogether.
- |  | · | · ​ ​The printable area of a tab does not fit on one page. In portrait view, it requires two pages to capture the width of the tab and in landscape view, it does not show the entire length of the page even with mutiple pages. There is also no way to edit printable views such and setting a print area or highlighting a selection and only printing selection. | Root cause | No fix needed | Reports should be printable, forms should not need to be printed. If there is an issue with a report, or report needed, that should be the task instead.
- |  | · | · DIU enter call PARIS - Applicant BROOKINGS 015-08650-00 - Missing exploratory call and RSM scheduled date and time. Reworked back to PDM to enter. Unknown if this is a PARIS issue. | Root cause | No fix needed | Seems more like a data issue.
- |  | · | · DIU Enter RSM - Linn County Road Management, When entering the information for the Scoping Meeting noticed there wasn't an area that contained the projections like in the Exploratory Call Info. The DIU processing tab has a box to click that reads "Scoping Meeting/Initial Projections Entered into EMMIE Complete". I believe there should be a tab or something to get the Projections so that they can be entered in the Projections area of the CMF. The Projections information in PARIS should mirror the CMF so that it can be entered into the corresponding fields. | Root cause | No fix needed | Projections in EMMIE are for single projects which comes after this step. Perhaps this should instead be that Paris projects should also be added to the EMMIE projecting list, but that seems duplicative and unnecessary.
- |  | · | · Exploratory Call - changed date, added comments, save/closed. Info was not saved. corrected when received back and submitted. Project Screen - to complete Routing sheet - ENTER PROJECTs has to be completed before the Enter Sites - then move ENTER PROJECTS before Enter Sites. Tried to do the Enter Sites first and did not populate properly. glitch disappeared afterwards. Enter List of Damages Screen - Select Applicant to Formulate Projects, clicked down to applicant, close form. Went back in and the Select applicant was blank. | Root cause | Unknown. | Switching “enter projects” and “enter sites” has been requested and switched both ways. Someone is always unhappy with the order. Other than the information not saving, I am not understanding the rest of the issue.
- |  | · | · ​ There is a disconnect between RPA eligibility in EMMIE and PARIS. RPAs are being marked eligible in EMMIE, but not in the process in PARIS so they are not being forwarded for PDM assignments, and as a result, Exploratory Calls tasks are not being created. This is also creating a disconnect between what leadership sees as applicants ready for a call, and what PDMs have been assigned. If this is the process going forward, recommend removing the RPA eligibility steps from PARIS entirely, and kicking them forward as they are marked eligible in EMMIE (which is already passed into PARIS). Otherwise, to ensure continuity in the process RPAs should not be marked eligible in EMMIE until they have cleared eligibility in PARIS. | Root cause | Duplicate | See above (item 2)
Low |  | · | · For recipient information, the same information has to be keyed in everytime. It would be helpful to have a list of the recipient information avaiable in a drop down instead of entry (perhaps as a disaster setup item). For many disasters there will only by the PAO to enter, but some states may have the state split into divisions. | Root cause | Medium fix | It will require a way to store the names and a way to do the dropdowns. Will be more complicated if other name boxes also need dropdowns.
Low |  | · | · Pressing tab from the Number of Complex Projects field on the Inital Projections form for the RSM creates a new blank record. | Root cause | Medium fix
High | Anisa | · | · When viewing completed exporatory calls and RSMs, the notes section only displays the first two lines and does not scroll. PDMs are unable to review their prior notes on applicants as a result. A scroll bar on the form (when completed), or a report with the notes is needed. | Root cause | Minor fix
- |  | · | · On the exploratory call form, need an option to enter an extension for the phone number.​ | Root cause | Done | This should be fixed in the current version.
High | Anisa | · | · There is a charcter limit on the exploratory call of about 210 characters. More space is needed to document details from the call. | Root cause | Minor fix | -This may be fixed currently. Will need to check which box exactly they are referring to.
1 |  | · | · Can’t send RFI and Site Inspection/Validation Work Order at the Same time | P. Kenney | Major fix | I will submit a list of questions for Sid and PK so that everyone is on the same page on how this will be implemented.
2 |  | · | · DIU can’t assign project to Standard TFL if send a Site Inspection Work Order (for 0% completed work with no documentation) | P. Kenney | Medium fix | As above, I submit the process for Sid and PK to give feedback on.
High | Nate - done | · | · Improve rework process in PARIS | Nate | Minor | This is regarding reworks going back to a specific person.
Low |  | · | · Integrate Categorical Information Checklist into PARIS | P. Kenney | 3 months | Incorporating the checklist so that it changed process flow is a major rework of the whole system. Call it something other than PARIS.
Medium |  | · | · Add ‘Date Assigned’ to “My Tasks” | DIU | minor
High | Nate | · | · Add comment section to reviews |  | Minor-medium | The issue is where the comment should be displayed.
- |  | · | · How to track partial responses to RFIs | DIU | Duplicate
Medium |  | · | · Process reflected in Expedtied Lane Phase III needs to be changed to reflect current process. |  | Minor | I think this is just referring to the name of the current “Costing” Review
Medium |  | · | · Include options for documents to request in RFI section |  | Medium? | Need clarification
- |  | · | · Allow DIU to enter RFIs (for 0% completed work) |  | Duplicate
- |  | · | · Add “% complete” and “as of” dates |  | Duplicate
Medium |  | · | · Timing should be GMT (to accurately track timing) |  | Major | Serious issue. The solutions possible are problematic based on their assumptions or problematic based on their required implementation.
High |  |  | Report that shows all project information (because PARIS screens may only show the most critical information…while the other information is on another screen behind the main page) |  | Medium | Would be useful in many areas and may act as stop-gap for other issues.
2 High | Anisa | Site inspection Assignment | Time box needs to be locked | PARIS team | Minor
2 High | Anisa .. Figure out which is best | StDvsSiteReview and subfrmProjectSites | Damage level dropdown needs consistency | PARIS team | Minor | Need clarification on what should be in there
2 High |  | ReviewResult | Rework should pass in the person to show in dropdown, and then assign that person | PARIS team | Duplicate
2 High | Nate | Exploratory call | DIU should not pop the date during RSN | PARIS team | Minor
2 High | Nate | DIU PRS | Switch to post check for lane selection | PARIS team | Minor
2 High |  | report navigation | error handling on all buttons | PARIS team | Medium
2 High |  | Multiple Review tasks | Rework and resubmittal is creating duplicate review tasks. Should check if an open one exists and only create if it doesn't. | PARIS team | Medium
2 High |  | Validation/SI/RFI | Redesign core functions so that RFI's,SI, and Validation can all happen simultanously | PARIS team | Duplicate
3 Medium |  | Site inspection Assignment | Inspection Notes should be relabeled to Special Instructions to the Inspector | PARIS team | Minor
3 Medium |  | Table fields | Anything that is a percent should be a single or double | PARIS team | Medium
3 Medium |  | Initial Projections | Have button to bring up Exploratory call report | PARIS team | Minor
3 Medium |  | Specialized Lane | Copy once Standard is finalized (add technical specialty) | PARIS team | Major
3 Medium |  | My tasks | add entry date as column | PARIS team | Duplicate
3 Medium |  | Review Module/All Forms | Standard Disposition | PARIS team | medium
4 Low |  | App Briefing | After one record has been successfully added, the new record does not have the proper disaster info | PARIS team | Minor
4 Low |  | Initial Projections | Add form behaviour | PARIS team | Duplicate
4 Low |  | Form Percent Fields | Don't show decimal point. Show rounded to nearest. | PARIS team | Minor-medium | It is a lot of fields to check
4 Low |  | Compliance review | Import from EDW | PARIS team | Medium
4 Low |  | Document Transmittal | implement | PARIS team | Major
4 Low |  | My tasks | Print out task list | PARIS team | Minor
4 Low |  | Note: | Ineligible applicant can be marked otherwise. Queries could filter them out. | PARIS team | Duplicate
4 Low |  | Exploratory Call | Create Post call report to email results to Applicant | PARIS team | Minor | Need format as an example first
4 Low |  | Exploratory Call | Checking Known EHP (for example) auto checks appropriate staff requests. | PARIS team | Minor
4 Low |  | subfrm tasks | don’t pass project id to applicant level project formulation form | PARIS team | Medium
4 Low |  | Check for Status | Put in label text for SITFL to explain why check status shows when it is not yet his project. | PARIS team | Minor (but see above)
2 High |  | Unit Testing | Develop process to check known issues before deployment | PARIS team | Medium
2 High |  | Git integration | Develop process for being able to work on the database simultaneously without having changes overwritten by one another. | PARIS team | Medium
4 Low |  | Navigation | Change how navigation works so scrolling projects is not needed | PARIS team | Major | Will require significant work, but was one of the major takeaways from the Denton Testing.